## PMP Quiz Results
Question Number | Question Text | Selected Answer | Correct Answer | Correct/Incorrect | Feedback
1 | An agile project is running activities to define the minimum viable product MVP. During the session, the project manager identifies some mandatory regulations, but there is no consensus to include these regulations in the MVP because if may extend the duration of the project. What should the project manager do? | Share with the participants the need to focus only on product functionality. | Get commitment from the team to include all of the required regulations. | Incorrect | In order to determine a usable product for the customer in each increment, the core value must be understood. Based on the essential value sought by the project, the bare minimum of how the value can be realized is established. As there are mandatory regulations that must be included, the project manager should get commitment from the team to include all of the required regulations.
2 | The project sponsor on an agile project informed the project lead that an executive would like an update on the project's progress. What should the project lead do? | Invite the executive to the project's meeting space to determine if the project information radiators met their needs. | Invite the executive to the project's meeting space to determine if the project information radiators met their needs. | Correct | Important Note for the real exam: an information radiator is a comprehensive display of key team Information openly shared with all team members and other stakeholders and continuously updated. It includes information such as the Kanban or task board, the team velocity, continuous integration status, the progress of the team, and Sprint Burn down Charts (when on walls). The project lead/ scrum master should Invite the executive to the project's meeting space to determine if the project information radiators meet their needs. An important question for PMP real exam.
3 | During the design phase, a project manager realizes that the project will benefit from using adaptive tools. The effectiveness of this approach has been proven in past projects inside the organization. What should the project manager do first? | Confirm team capabilities before introducing adaptive tools and artefacts to the project | Confirm team capabilities before introducing adaptive tools and artefacts to the project | Correct | As mentioned in the question (FIRST) The project manager should first Confirm team capabilities before introducing adaptive tools and artifacts to the project to see if the team needs training or ask the company to provide skilled, experienced team members.
4 | Which of the following reflect key values listed in the Agile Manifesto? (Select all that apply.) | Individuals and interactions over processes and tools; Customer collaboration over contract negotiation; Responding to change over following a plan; Evolving software over comprehensive documentation | Individuals and interactions over processes and tools; Customer collaboration over contract negotiation; Responding to change over following a plan; Evolving software over comprehensive documentation | Correct | The Agile Manifesto for Software Development was published in 2001 by thought leaders in the software industry. The intent was to propose a new way of developing software. It consists of 12 principles and 4 key values.
5 | A company has a lot of experience with predictive project the project management office (PMO) has been trying to implement iterative tools within the project management framework, and the project manager has been asked to use these tools in their current project, after the successful implementation of the iterative tools, the PMO asks the project manager to determine the benefits these tools brought to the project. What should the project manager do? | Determine the data to be monitored during the project as well as the expected performance and targets. | Conduct reviews with stakeholders to discuss the potential benefits the approach may have to the project | Incorrect | Conduct reviews with stakeholders to discuss the potential benefits the approach may have to the project.