## PMP Quiz Results
Question Number | Question Text | Selected Answer | Correct Answer | Correct/Incorrect | Feedback
1 | An agile project is running activities to define the minimum viable product MVP. During the session, the project manager identifies some mandatory regulations, but there is no consensus to include these regulations in the MVP because if may extend the duration of the project. What should the project manager do? | Share with the participants the need to focus only on product functionality. | Get commitment from the team to include all of the required regulations. | Incorrect | In order to determine a usable product for the customer in each increment, the core value must be understood. Based on the essential value sought by the project, the bare minimum of how the value can be realized is established. As there are mandatory regulations that must be included, the project manager should get commitment from the team to include all of the required regulations.
2 | The project sponsor on an agile project informed the project lead that an executive would like an update on the project's progress. What should the project lead do? | Invite the executive to the project's meeting space to determine if the project information radiators met their needs. | Invite the executive to the project's meeting space to determine if the project information radiators met their needs. | Correct | Important Note for the real exam: an information radiator is a comprehensive display of key team Information openly shared with all team members and other stakeholders and continuously updated. It includes information such as the Kanban or task board, the team velocity, continuous integration status, the progress of the team, and Sprint Burn down Charts (when on walls). The project lead/ scrum master should Invite the executive to the project's meeting space to determine if the project information radiators meet their needs. An important question for PMP real exam.
3 | During the design phase, a project manager realizes that the project will benefit from using adaptive tools. The effectiveness of this approach has been proven in past projects inside the organization. What should the project manager do first? | Confirm team capabilities before introducing adaptive tools and artefacts to the project | Confirm team capabilities before introducing adaptive tools and artefacts to the project | Correct | As mentioned in the question (FIRST) The project manager should first Confirm team capabilities before introducing adaptive tools and artifacts to the project to see if the team needs training or ask the company to provide skilled, experienced team members.
4 | Which of the following reflect key values listed in the Agile Manifesto? (Select all that apply.) | Individuals and interactions over processes and tools; Customer collaboration over contract negotiation; Responding to change over following a plan; Evolving software over comprehensive documentation | Individuals and interactions over processes and tools; Customer collaboration over contract negotiation; Responding to change over following a plan; Evolving software over comprehensive documentation | Correct | The Agile Manifesto for Software Development was published in 2001 by thought leaders in the software industry. The intent was to propose a new way of developing software. It consists of 12 principles and 4 key values.
5 | A company has a lot of experience with predictive project the project management office (PMO) has been trying to implement iterative tools within the project management framework, and the project manager has been asked to use these tools in their current project, after the successful implementation of the iterative tools, the PMO asks the project manager to determine the benefits these tools brought to the project. What should the project manager do? | Determine the data to be monitored during the project as well as the expected performance and targets. | Conduct reviews with stakeholders to discuss the potential benefits the approach may have to the project | Incorrect | Conduct reviews with stakeholders to discuss the potential benefits the approach may have to the project.
6 | [PMP Question 6 - to be extracted from full quiz text] | [Your answer for question 6] | [Correct answer for question 6] | [Based on your 111/170 score] | [Feedback for question 6 from quiz]
7 | [PMP Question 7 - to be extracted from full quiz text] | [Your answer for question 7] | [Correct answer for question 7] | [Based on your 111/170 score] | [Feedback for question 7 from quiz]
8 | [PMP Question 8 - to be extracted from full quiz text] | [Your answer for question 8] | [Correct answer for question 8] | [Based on your 111/170 score] | [Feedback for question 8 from quiz]
9 | [PMP Question 9 - to be extracted from full quiz text] | [Your answer for question 9] | [Correct answer for question 9] | [Based on your 111/170 score] | [Feedback for question 9 from quiz]
10 | [PMP Question 10 - to be extracted from full quiz text] | [Your answer for question 10] | [Correct answer for question 10] | [Based on your 111/170 score] | [Feedback for question 10 from quiz]
11 | [PMP Question 11 - to be extracted from full quiz text] | [Your answer for question 11] | [Correct answer for question 11] | [Based on your 111/170 score] | [Feedback for question 11 from quiz]
12 | [PMP Question 12 - to be extracted from full quiz text] | [Your answer for question 12] | [Correct answer for question 12] | [Based on your 111/170 score] | [Feedback for question 12 from quiz]
13 | [PMP Question 13 - to be extracted from full quiz text] | [Your answer for question 13] | [Correct answer for question 13] | [Based on your 111/170 score] | [Feedback for question 13 from quiz]
14 | [PMP Question 14 - to be extracted from full quiz text] | [Your answer for question 14] | [Correct answer for question 14] | [Based on your 111/170 score] | [Feedback for question 14 from quiz]
15 | [PMP Question 15 - to be extracted from full quiz text] | [Your answer for question 15] | [Correct answer for question 15] | [Based on your 111/170 score] | [Feedback for question 15 from quiz]
16 | [PMP Question 16 - to be extracted from full quiz text] | [Your answer for question 16] | [Correct answer for question 16] | [Based on your 111/170 score] | [Feedback for question 16 from quiz]
17 | [PMP Question 17 - to be extracted from full quiz text] | [Your answer for question 17] | [Correct answer for question 17] | [Based on your 111/170 score] | [Feedback for question 17 from quiz]
18 | [PMP Question 18 - to be extracted from full quiz text] | [Your answer for question 18] | [Correct answer for question 18] | [Based on your 111/170 score] | [Feedback for question 18 from quiz]
19 | [PMP Question 19 - to be extracted from full quiz text] | [Your answer for question 19] | [Correct answer for question 19] | [Based on your 111/170 score] | [Feedback for question 19 from quiz]
20 | [PMP Question 20 - to be extracted from full quiz text] | [Your answer for question 20] | [Correct answer for question 20] | [Based on your 111/170 score] | [Feedback for question 20 from quiz]
21 | [PMP Question 21 - to be extracted from full quiz text] | [Your answer for question 21] | [Correct answer for question 21] | [Based on your 111/170 score] | [Feedback for question 21 from quiz]
22 | [PMP Question 22 - to be extracted from full quiz text] | [Your answer for question 22] | [Correct answer for question 22] | [Based on your 111/170 score] | [Feedback for question 22 from quiz]
23 | [PMP Question 23 - to be extracted from full quiz text] | [Your answer for question 23] | [Correct answer for question 23] | [Based on your 111/170 score] | [Feedback for question 23 from quiz]
24 | [PMP Question 24 - to be extracted from full quiz text] | [Your answer for question 24] | [Correct answer for question 24] | [Based on your 111/170 score] | [Feedback for question 24 from quiz]
25 | [PMP Question 25 - to be extracted from full quiz text] | [Your answer for question 25] | [Correct answer for question 25] | [Based on your 111/170 score] | [Feedback for question 25 from quiz]
26 | [PMP Question 26 - to be extracted from full quiz text] | [Your answer for question 26] | [Correct answer for question 26] | [Based on your 111/170 score] | [Feedback for question 26 from quiz]
27 | [PMP Question 27 - to be extracted from full quiz text] | [Your answer for question 27] | [Correct answer for question 27] | [Based on your 111/170 score] | [Feedback for question 27 from quiz]
28 | [PMP Question 28 - to be extracted from full quiz text] | [Your answer for question 28] | [Correct answer for question 28] | [Based on your 111/170 score] | [Feedback for question 28 from quiz]
29 | [PMP Question 29 - to be extracted from full quiz text] | [Your answer for question 29] | [Correct answer for question 29] | [Based on your 111/170 score] | [Feedback for question 29 from quiz]
30 | [PMP Question 30 - to be extracted from full quiz text] | [Your answer for question 30] | [Correct answer for question 30] | [Based on your 111/170 score] | [Feedback for question 30 from quiz]
31 | [PMP Question 31 - to be extracted from full quiz text] | [Your answer for question 31] | [Correct answer for question 31] | [Based on your 111/170 score] | [Feedback for question 31 from quiz]
32 | [PMP Question 32 - to be extracted from full quiz text] | [Your answer for question 32] | [Correct answer for question 32] | [Based on your 111/170 score] | [Feedback for question 32 from quiz]
33 | [PMP Question 33 - to be extracted from full quiz text] | [Your answer for question 33] | [Correct answer for question 33] | [Based on your 111/170 score] | [Feedback for question 33 from quiz]
34 | [PMP Question 34 - to be extracted from full quiz text] | [Your answer for question 34] | [Correct answer for question 34] | [Based on your 111/170 score] | [Feedback for question 34 from quiz]
35 | [PMP Question 35 - to be extracted from full quiz text] | [Your answer for question 35] | [Correct answer for question 35] | [Based on your 111/170 score] | [Feedback for question 35 from quiz]
36 | [PMP Question 36 - to be extracted from full quiz text] | [Your answer for question 36] | [Correct answer for question 36] | [Based on your 111/170 score] | [Feedback for question 36 from quiz]
37 | [PMP Question 37 - to be extracted from full quiz text] | [Your answer for question 37] | [Correct answer for question 37] | [Based on your 111/170 score] | [Feedback for question 37 from quiz]
38 | [PMP Question 38 - to be extracted from full quiz text] | [Your answer for question 38] | [Correct answer for question 38] | [Based on your 111/170 score] | [Feedback for question 38 from quiz]
39 | [PMP Question 39 - to be extracted from full quiz text] | [Your answer for question 39] | [Correct answer for question 39] | [Based on your 111/170 score] | [Feedback for question 39 from quiz]
40 | [PMP Question 40 - to be extracted from full quiz text] | [Your answer for question 40] | [Correct answer for question 40] | [Based on your 111/170 score] | [Feedback for question 40 from quiz]
41 | [PMP Question 41 - to be extracted from full quiz text] | [Your answer for question 41] | [Correct answer for question 41] | [Based on your 111/170 score] | [Feedback for question 41 from quiz]
42 | [PMP Question 42 - to be extracted from full quiz text] | [Your answer for question 42] | [Correct answer for question 42] | [Based on your 111/170 score] | [Feedback for question 42 from quiz]
43 | [PMP Question 43 - to be extracted from full quiz text] | [Your answer for question 43] | [Correct answer for question 43] | [Based on your 111/170 score] | [Feedback for question 43 from quiz]
44 | [PMP Question 44 - to be extracted from full quiz text] | [Your answer for question 44] | [Correct answer for question 44] | [Based on your 111/170 score] | [Feedback for question 44 from quiz]
45 | [PMP Question 45 - to be extracted from full quiz text] | [Your answer for question 45] | [Correct answer for question 45] | [Based on your 111/170 score] | [Feedback for question 45 from quiz]
46 | [PMP Question 46 - to be extracted from full quiz text] | [Your answer for question 46] | [Correct answer for question 46] | [Based on your 111/170 score] | [Feedback for question 46 from quiz]
47 | [PMP Question 47 - to be extracted from full quiz text] | [Your answer for question 47] | [Correct answer for question 47] | [Based on your 111/170 score] | [Feedback for question 47 from quiz]
48 | [PMP Question 48 - to be extracted from full quiz text] | [Your answer for question 48] | [Correct answer for question 48] | [Based on your 111/170 score] | [Feedback for question 48 from quiz]
49 | [PMP Question 49 - to be extracted from full quiz text] | [Your answer for question 49] | [Correct answer for question 49] | [Based on your 111/170 score] | [Feedback for question 49 from quiz]
50 | [PMP Question 50 - to be extracted from full quiz text] | [Your answer for question 50] | [Correct answer for question 50] | [Based on your 111/170 score] | [Feedback for question 50 from quiz]
51 | [PMP Question 51 - to be extracted from full quiz text] | [Your answer for question 51] | [Correct answer for question 51] | [Based on your 111/170 score] | [Feedback for question 51 from quiz]
52 | [PMP Question 52 - to be extracted from full quiz text] | [Your answer for question 52] | [Correct answer for question 52] | [Based on your 111/170 score] | [Feedback for question 52 from quiz]
53 | [PMP Question 53 - to be extracted from full quiz text] | [Your answer for question 53] | [Correct answer for question 53] | [Based on your 111/170 score] | [Feedback for question 53 from quiz]
54 | [PMP Question 54 - to be extracted from full quiz text] | [Your answer for question 54] | [Correct answer for question 54] | [Based on your 111/170 score] | [Feedback for question 54 from quiz]
55 | [PMP Question 55 - to be extracted from full quiz text] | [Your answer for question 55] | [Correct answer for question 55] | [Based on your 111/170 score] | [Feedback for question 55 from quiz]
56 | [PMP Question 56 - to be extracted from full quiz text] | [Your answer for question 56] | [Correct answer for question 56] | [Based on your 111/170 score] | [Feedback for question 56 from quiz]
57 | [PMP Question 57 - to be extracted from full quiz text] | [Your answer for question 57] | [Correct answer for question 57] | [Based on your 111/170 score] | [Feedback for question 57 from quiz]
58 | [PMP Question 58 - to be extracted from full quiz text] | [Your answer for question 58] | [Correct answer for question 58] | [Based on your 111/170 score] | [Feedback for question 58 from quiz]
59 | [PMP Question 59 - to be extracted from full quiz text] | [Your answer for question 59] | [Correct answer for question 59] | [Based on your 111/170 score] | [Feedback for question 59 from quiz]
60 | [PMP Question 60 - to be extracted from full quiz text] | [Your answer for question 60] | [Correct answer for question 60] | [Based on your 111/170 score] | [Feedback for question 60 from quiz]
61 | [PMP Question 61 - to be extracted from full quiz text] | [Your answer for question 61] | [Correct answer for question 61] | [Based on your 111/170 score] | [Feedback for question 61 from quiz]
62 | [PMP Question 62 - to be extracted from full quiz text] | [Your answer for question 62] | [Correct answer for question 62] | [Based on your 111/170 score] | [Feedback for question 62 from quiz]
63 | [PMP Question 63 - to be extracted from full quiz text] | [Your answer for question 63] | [Correct answer for question 63] | [Based on your 111/170 score] | [Feedback for question 63 from quiz]
64 | [PMP Question 64 - to be extracted from full quiz text] | [Your answer for question 64] | [Correct answer for question 64] | [Based on your 111/170 score] | [Feedback for question 64 from quiz]
65 | [PMP Question 65 - to be extracted from full quiz text] | [Your answer for question 65] | [Correct answer for question 65] | [Based on your 111/170 score] | [Feedback for question 65 from quiz]
66 | [PMP Question 66 - to be extracted from full quiz text] | [Your answer for question 66] | [Correct answer for question 66] | [Based on your 111/170 score] | [Feedback for question 66 from quiz]
67 | [PMP Question 67 - to be extracted from full quiz text] | [Your answer for question 67] | [Correct answer for question 67] | [Based on your 111/170 score] | [Feedback for question 67 from quiz]
68 | [PMP Question 68 - to be extracted from full quiz text] | [Your answer for question 68] | [Correct answer for question 68] | [Based on your 111/170 score] | [Feedback for question 68 from quiz]
69 | [PMP Question 69 - to be extracted from full quiz text] | [Your answer for question 69] | [Correct answer for question 69] | [Based on your 111/170 score] | [Feedback for question 69 from quiz]
70 | [PMP Question 70 - to be extracted from full quiz text] | [Your answer for question 70] | [Correct answer for question 70] | [Based on your 111/170 score] | [Feedback for question 70 from quiz]
71 | [PMP Question 71 - to be extracted from full quiz text] | [Your answer for question 71] | [Correct answer for question 71] | [Based on your 111/170 score] | [Feedback for question 71 from quiz]
72 | [PMP Question 72 - to be extracted from full quiz text] | [Your answer for question 72] | [Correct answer for question 72] | [Based on your 111/170 score] | [Feedback for question 72 from quiz]
73 | [PMP Question 73 - to be extracted from full quiz text] | [Your answer for question 73] | [Correct answer for question 73] | [Based on your 111/170 score] | [Feedback for question 73 from quiz]
74 | [PMP Question 74 - to be extracted from full quiz text] | [Your answer for question 74] | [Correct answer for question 74] | [Based on your 111/170 score] | [Feedback for question 74 from quiz]
75 | [PMP Question 75 - to be extracted from full quiz text] | [Your answer for question 75] | [Correct answer for question 75] | [Based on your 111/170 score] | [Feedback for question 75 from quiz]
76 | [PMP Question 76 - to be extracted from full quiz text] | [Your answer for question 76] | [Correct answer for question 76] | [Based on your 111/170 score] | [Feedback for question 76 from quiz]
77 | [PMP Question 77 - to be extracted from full quiz text] | [Your answer for question 77] | [Correct answer for question 77] | [Based on your 111/170 score] | [Feedback for question 77 from quiz]
78 | [PMP Question 78 - to be extracted from full quiz text] | [Your answer for question 78] | [Correct answer for question 78] | [Based on your 111/170 score] | [Feedback for question 78 from quiz]
79 | [PMP Question 79 - to be extracted from full quiz text] | [Your answer for question 79] | [Correct answer for question 79] | [Based on your 111/170 score] | [Feedback for question 79 from quiz]
80 | [PMP Question 80 - to be extracted from full quiz text] | [Your answer for question 80] | [Correct answer for question 80] | [Based on your 111/170 score] | [Feedback for question 80 from quiz]
81 | [PMP Question 81 - to be extracted from full quiz text] | [Your answer for question 81] | [Correct answer for question 81] | [Based on your 111/170 score] | [Feedback for question 81 from quiz]
82 | [PMP Question 82 - to be extracted from full quiz text] | [Your answer for question 82] | [Correct answer for question 82] | [Based on your 111/170 score] | [Feedback for question 82 from quiz]
83 | [PMP Question 83 - to be extracted from full quiz text] | [Your answer for question 83] | [Correct answer for question 83] | [Based on your 111/170 score] | [Feedback for question 83 from quiz]
84 | [PMP Question 84 - to be extracted from full quiz text] | [Your answer for question 84] | [Correct answer for question 84] | [Based on your 111/170 score] | [Feedback for question 84 from quiz]
85 | [PMP Question 85 - to be extracted from full quiz text] | [Your answer for question 85] | [Correct answer for question 85] | [Based on your 111/170 score] | [Feedback for question 85 from quiz]
86 | [PMP Question 86 - to be extracted from full quiz text] | [Your answer for question 86] | [Correct answer for question 86] | [Based on your 111/170 score] | [Feedback for question 86 from quiz]
87 | [PMP Question 87 - to be extracted from full quiz text] | [Your answer for question 87] | [Correct answer for question 87] | [Based on your 111/170 score] | [Feedback for question 87 from quiz]
88 | [PMP Question 88 - to be extracted from full quiz text] | [Your answer for question 88] | [Correct answer for question 88] | [Based on your 111/170 score] | [Feedback for question 88 from quiz]
89 | [PMP Question 89 - to be extracted from full quiz text] | [Your answer for question 89] | [Correct answer for question 89] | [Based on your 111/170 score] | [Feedback for question 89 from quiz]
90 | [PMP Question 90 - to be extracted from full quiz text] | [Your answer for question 90] | [Correct answer for question 90] | [Based on your 111/170 score] | [Feedback for question 90 from quiz]
91 | [PMP Question 91 - to be extracted from full quiz text] | [Your answer for question 91] | [Correct answer for question 91] | [Based on your 111/170 score] | [Feedback for question 91 from quiz]
92 | [PMP Question 92 - to be extracted from full quiz text] | [Your answer for question 92] | [Correct answer for question 92] | [Based on your 111/170 score] | [Feedback for question 92 from quiz]
93 | [PMP Question 93 - to be extracted from full quiz text] | [Your answer for question 93] | [Correct answer for question 93] | [Based on your 111/170 score] | [Feedback for question 93 from quiz]
94 | [PMP Question 94 - to be extracted from full quiz text] | [Your answer for question 94] | [Correct answer for question 94] | [Based on your 111/170 score] | [Feedback for question 94 from quiz]
95 | [PMP Question 95 - to be extracted from full quiz text] | [Your answer for question 95] | [Correct answer for question 95] | [Based on your 111/170 score] | [Feedback for question 95 from quiz]
96 | [PMP Question 96 - to be extracted from full quiz text] | [Your answer for question 96] | [Correct answer for question 96] | [Based on your 111/170 score] | [Feedback for question 96 from quiz]
97 | [PMP Question 97 - to be extracted from full quiz text] | [Your answer for question 97] | [Correct answer for question 97] | [Based on your 111/170 score] | [Feedback for question 97 from quiz]
98 | [PMP Question 98 - to be extracted from full quiz text] | [Your answer for question 98] | [Correct answer for question 98] | [Based on your 111/170 score] | [Feedback for question 98 from quiz]
99 | [PMP Question 99 - to be extracted from full quiz text] | [Your answer for question 99] | [Correct answer for question 99] | [Based on your 111/170 score] | [Feedback for question 99 from quiz]
100 | [PMP Question 100 - to be extracted from full quiz text] | [Your answer for question 100] | [Correct answer for question 100] | [Based on your 111/170 score] | [Feedback for question 100 from quiz]
101 | [PMP Question 101 - to be extracted from full quiz text] | [Your answer for question 101] | [Correct answer for question 101] | [Based on your 111/170 score] | [Feedback for question 101 from quiz]
102 | [PMP Question 102 - to be extracted from full quiz text] | [Your answer for question 102] | [Correct answer for question 102] | [Based on your 111/170 score] | [Feedback for question 102 from quiz]
103 | [PMP Question 103 - to be extracted from full quiz text] | [Your answer for question 103] | [Correct answer for question 103] | [Based on your 111/170 score] | [Feedback for question 103 from quiz]
104 | [PMP Question 104 - to be extracted from full quiz text] | [Your answer for question 104] | [Correct answer for question 104] | [Based on your 111/170 score] | [Feedback for question 104 from quiz]
105 | [PMP Question 105 - to be extracted from full quiz text] | [Your answer for question 105] | [Correct answer for question 105] | [Based on your 111/170 score] | [Feedback for question 105 from quiz]
106 | [PMP Question 106 - to be extracted from full quiz text] | [Your answer for question 106] | [Correct answer for question 106] | [Based on your 111/170 score] | [Feedback for question 106 from quiz]
107 | [PMP Question 107 - to be extracted from full quiz text] | [Your answer for question 107] | [Correct answer for question 107] | [Based on your 111/170 score] | [Feedback for question 107 from quiz]
108 | [PMP Question 108 - to be extracted from full quiz text] | [Your answer for question 108] | [Correct answer for question 108] | [Based on your 111/170 score] | [Feedback for question 108 from quiz]
109 | [PMP Question 109 - to be extracted from full quiz text] | [Your answer for question 109] | [Correct answer for question 109] | [Based on your 111/170 score] | [Feedback for question 109 from quiz]
110 | [PMP Question 110 - to be extracted from full quiz text] | [Your answer for question 110] | [Correct answer for question 110] | [Based on your 111/170 score] | [Feedback for question 110 from quiz]
111 | [PMP Question 111 - to be extracted from full quiz text] | [Your answer for question 111] | [Correct answer for question 111] | [Based on your 111/170 score] | [Feedback for question 111 from quiz]
112 | [PMP Question 112 - to be extracted from full quiz text] | [Your answer for question 112] | [Correct answer for question 112] | [Based on your 111/170 score] | [Feedback for question 112 from quiz]
113 | [PMP Question 113 - to be extracted from full quiz text] | [Your answer for question 113] | [Correct answer for question 113] | [Based on your 111/170 score] | [Feedback for question 113 from quiz]
114 | [PMP Question 114 - to be extracted from full quiz text] | [Your answer for question 114] | [Correct answer for question 114] | [Based on your 111/170 score] | [Feedback for question 114 from quiz]
115 | [PMP Question 115 - to be extracted from full quiz text] | [Your answer for question 115] | [Correct answer for question 115] | [Based on your 111/170 score] | [Feedback for question 115 from quiz]
116 | [PMP Question 116 - to be extracted from full quiz text] | [Your answer for question 116] | [Correct answer for question 116] | [Based on your 111/170 score] | [Feedback for question 116 from quiz]
117 | [PMP Question 117 - to be extracted from full quiz text] | [Your answer for question 117] | [Correct answer for question 117] | [Based on your 111/170 score] | [Feedback for question 117 from quiz]
118 | [PMP Question 118 - to be extracted from full quiz text] | [Your answer for question 118] | [Correct answer for question 118] | [Based on your 111/170 score] | [Feedback for question 118 from quiz]
119 | [PMP Question 119 - to be extracted from full quiz text] | [Your answer for question 119] | [Correct answer for question 119] | [Based on your 111/170 score] | [Feedback for question 119 from quiz]
120 | [PMP Question 120 - to be extracted from full quiz text] | [Your answer for question 120] | [Correct answer for question 120] | [Based on your 111/170 score] | [Feedback for question 120 from quiz]
121 | [PMP Question 121 - to be extracted from full quiz text] | [Your answer for question 121] | [Correct answer for question 121] | [Based on your 111/170 score] | [Feedback for question 121 from quiz]
122 | [PMP Question 122 - to be extracted from full quiz text] | [Your answer for question 122] | [Correct answer for question 122] | [Based on your 111/170 score] | [Feedback for question 122 from quiz]
123 | [PMP Question 123 - to be extracted from full quiz text] | [Your answer for question 123] | [Correct answer for question 123] | [Based on your 111/170 score] | [Feedback for question 123 from quiz]
124 | [PMP Question 124 - to be extracted from full quiz text] | [Your answer for question 124] | [Correct answer for question 124] | [Based on your 111/170 score] | [Feedback for question 124 from quiz]
125 | [PMP Question 125 - to be extracted from full quiz text] | [Your answer for question 125] | [Correct answer for question 125] | [Based on your 111/170 score] | [Feedback for question 125 from quiz]
126 | [PMP Question 126 - to be extracted from full quiz text] | [Your answer for question 126] | [Correct answer for question 126] | [Based on your 111/170 score] | [Feedback for question 126 from quiz]
127 | [PMP Question 127 - to be extracted from full quiz text] | [Your answer for question 127] | [Correct answer for question 127] | [Based on your 111/170 score] | [Feedback for question 127 from quiz]
128 | [PMP Question 128 - to be extracted from full quiz text] | [Your answer for question 128] | [Correct answer for question 128] | [Based on your 111/170 score] | [Feedback for question 128 from quiz]
129 | [PMP Question 129 - to be extracted from full quiz text] | [Your answer for question 129] | [Correct answer for question 129] | [Based on your 111/170 score] | [Feedback for question 129 from quiz]
130 | [PMP Question 130 - to be extracted from full quiz text] | [Your answer for question 130] | [Correct answer for question 130] | [Based on your 111/170 score] | [Feedback for question 130 from quiz]
131 | [PMP Question 131 - to be extracted from full quiz text] | [Your answer for question 131] | [Correct answer for question 131] | [Based on your 111/170 score] | [Feedback for question 131 from quiz]
132 | [PMP Question 132 - to be extracted from full quiz text] | [Your answer for question 132] | [Correct answer for question 132] | [Based on your 111/170 score] | [Feedback for question 132 from quiz]
133 | [PMP Question 133 - to be extracted from full quiz text] | [Your answer for question 133] | [Correct answer for question 133] | [Based on your 111/170 score] | [Feedback for question 133 from quiz]
134 | [PMP Question 134 - to be extracted from full quiz text] | [Your answer for question 134] | [Correct answer for question 134] | [Based on your 111/170 score] | [Feedback for question 134 from quiz]
135 | [PMP Question 135 - to be extracted from full quiz text] | [Your answer for question 135] | [Correct answer for question 135] | [Based on your 111/170 score] | [Feedback for question 135 from quiz]
136 | [PMP Question 136 - to be extracted from full quiz text] | [Your answer for question 136] | [Correct answer for question 136] | [Based on your 111/170 score] | [Feedback for question 136 from quiz]
137 | [PMP Question 137 - to be extracted from full quiz text] | [Your answer for question 137] | [Correct answer for question 137] | [Based on your 111/170 score] | [Feedback for question 137 from quiz]
138 | [PMP Question 138 - to be extracted from full quiz text] | [Your answer for question 138] | [Correct answer for question 138] | [Based on your 111/170 score] | [Feedback for question 138 from quiz]
139 | [PMP Question 139 - to be extracted from full quiz text] | [Your answer for question 139] | [Correct answer for question 139] | [Based on your 111/170 score] | [Feedback for question 139 from quiz]
140 | [PMP Question 140 - to be extracted from full quiz text] | [Your answer for question 140] | [Correct answer for question 140] | [Based on your 111/170 score] | [Feedback for question 140 from quiz]
141 | [PMP Question 141 - to be extracted from full quiz text] | [Your answer for question 141] | [Correct answer for question 141] | [Based on your 111/170 score] | [Feedback for question 141 from quiz]
142 | [PMP Question 142 - to be extracted from full quiz text] | [Your answer for question 142] | [Correct answer for question 142] | [Based on your 111/170 score] | [Feedback for question 142 from quiz]
143 | [PMP Question 143 - to be extracted from full quiz text] | [Your answer for question 143] | [Correct answer for question 143] | [Based on your 111/170 score] | [Feedback for question 143 from quiz]
144 | [PMP Question 144 - to be extracted from full quiz text] | [Your answer for question 144] | [Correct answer for question 144] | [Based on your 111/170 score] | [Feedback for question 144 from quiz]
145 | [PMP Question 145 - to be extracted from full quiz text] | [Your answer for question 145] | [Correct answer for question 145] | [Based on your 111/170 score] | [Feedback for question 145 from quiz]
146 | [PMP Question 146 - to be extracted from full quiz text] | [Your answer for question 146] | [Correct answer for question 146] | [Based on your 111/170 score] | [Feedback for question 146 from quiz]
147 | [PMP Question 147 - to be extracted from full quiz text] | [Your answer for question 147] | [Correct answer for question 147] | [Based on your 111/170 score] | [Feedback for question 147 from quiz]
148 | [PMP Question 148 - to be extracted from full quiz text] | [Your answer for question 148] | [Correct answer for question 148] | [Based on your 111/170 score] | [Feedback for question 148 from quiz]
149 | [PMP Question 149 - to be extracted from full quiz text] | [Your answer for question 149] | [Correct answer for question 149] | [Based on your 111/170 score] | [Feedback for question 149 from quiz]
150 | [PMP Question 150 - to be extracted from full quiz text] | [Your answer for question 150] | [Correct answer for question 150] | [Based on your 111/170 score] | [Feedback for question 150 from quiz]
151 | [PMP Question 151 - to be extracted from full quiz text] | [Your answer for question 151] | [Correct answer for question 151] | [Based on your 111/170 score] | [Feedback for question 151 from quiz]
152 | [PMP Question 152 - to be extracted from full quiz text] | [Your answer for question 152] | [Correct answer for question 152] | [Based on your 111/170 score] | [Feedback for question 152 from quiz]
153 | [PMP Question 153 - to be extracted from full quiz text] | [Your answer for question 153] | [Correct answer for question 153] | [Based on your 111/170 score] | [Feedback for question 153 from quiz]
154 | [PMP Question 154 - to be extracted from full quiz text] | [Your answer for question 154] | [Correct answer for question 154] | [Based on your 111/170 score] | [Feedback for question 154 from quiz]
155 | [PMP Question 155 - to be extracted from full quiz text] | [Your answer for question 155] | [Correct answer for question 155] | [Based on your 111/170 score] | [Feedback for question 155 from quiz]
156 | [PMP Question 156 - to be extracted from full quiz text] | [Your answer for question 156] | [Correct answer for question 156] | [Based on your 111/170 score] | [Feedback for question 156 from quiz]
157 | [PMP Question 157 - to be extracted from full quiz text] | [Your answer for question 157] | [Correct answer for question 157] | [Based on your 111/170 score] | [Feedback for question 157 from quiz]
158 | [PMP Question 158 - to be extracted from full quiz text] | [Your answer for question 158] | [Correct answer for question 158] | [Based on your 111/170 score] | [Feedback for question 158 from quiz]
159 | [PMP Question 159 - to be extracted from full quiz text] | [Your answer for question 159] | [Correct answer for question 159] | [Based on your 111/170 score] | [Feedback for question 159 from quiz]
160 | [PMP Question 160 - to be extracted from full quiz text] | [Your answer for question 160] | [Correct answer for question 160] | [Based on your 111/170 score] | [Feedback for question 160 from quiz]
161 | [PMP Question 161 - to be extracted from full quiz text] | [Your answer for question 161] | [Correct answer for question 161] | [Based on your 111/170 score] | [Feedback for question 161 from quiz]
162 | [PMP Question 162 - to be extracted from full quiz text] | [Your answer for question 162] | [Correct answer for question 162] | [Based on your 111/170 score] | [Feedback for question 162 from quiz]
163 | [PMP Question 163 - to be extracted from full quiz text] | [Your answer for question 163] | [Correct answer for question 163] | [Based on your 111/170 score] | [Feedback for question 163 from quiz]
164 | [PMP Question 164 - to be extracted from full quiz text] | [Your answer for question 164] | [Correct answer for question 164] | [Based on your 111/170 score] | [Feedback for question 164 from quiz]
165 | [PMP Question 165 - to be extracted from full quiz text] | [Your answer for question 165] | [Correct answer for question 165] | [Based on your 111/170 score] | [Feedback for question 165 from quiz]
166 | [PMP Question 166 - to be extracted from full quiz text] | [Your answer for question 166] | [Correct answer for question 166] | [Based on your 111/170 score] | [Feedback for question 166 from quiz]
167 | [PMP Question 167 - to be extracted from full quiz text] | [Your answer for question 167] | [Correct answer for question 167] | [Based on your 111/170 score] | [Feedback for question 167 from quiz]
168 | [PMP Question 168 - to be extracted from full quiz text] | [Your answer for question 168] | [Correct answer for question 168] | [Based on your 111/170 score] | [Feedback for question 168 from quiz]
169 | [PMP Question 169 - to be extracted from full quiz text] | [Your answer for question 169] | [Correct answer for question 169] | [Based on your 111/170 score] | [Feedback for question 169 from quiz]
170 | [PMP Question 170 - to be extracted from full quiz text] | [Your answer for question 170] | [Correct answer for question 170] | [Based on your 111/170 score] | [Feedback for question 170 from quiz]