## PMP Quiz Results
Question Number | Question Text | Selected Answer | Correct Answer | Correct/Incorrect | Feedback
1 | An agile project is running activities to define the minimum viable product MVP. During the session, the project manager identifies some mandatory regulations, but there is no consensus to include these regulations in the MVP because if may extend the duration of the project. What should the project manager do? | Share with the participants the need to focus only on product functionality. | Get commitment from the team to include all of the required regulations. | Incorrect | In order to determine a usable product for the customer in each increment, the core value must be understood. Based on the essential value sought by the project, the bare minimum of how the value can be realized is established. As there are mandatory regulations that must be included, the project manager should get commitment from the team to include all of the required regulations.
2 | The project sponsor on an agile project informed the project lead that an executive would like an update on the project's progress. What should the project lead do? | Invite the executive to the project's meeting space to determine if the project information radiators met their needs. | Invite the executive to the project's meeting space to determine if the project information radiators met their needs. | Correct | Important Note for the real exam: an information radiator is a comprehensive display of key team Information openly shared with all team members and other stakeholders and continuously updated. It includes information such as the Kanban or task board, the team velocity, continuous integration status, the progress of the team, and Sprint Burn down Charts (when on walls). The project lead/ scrum master should Invite the executive to the project's meeting space to determine if the project information radiators meet their needs. An important question for PMP real exam.
3 | During the design phase, a project manager realizes that the project will benefit from using adaptive tools. The effectiveness of this approach has been proven in past projects inside the organization. What should the project manager do first? | Confirm team capabilities before introducing adaptive tools and artefacts to the project | Confirm team capabilities before introducing adaptive tools and artefacts to the project | Correct | As mentioned in the question (FIRST) The project manager should first Confirm team capabilities before introducing adaptive tools and artifacts to the project to see if the team needs training or ask the company to provide skilled, experienced team members.
4 | Which of the following reflect key values listed in the Agile Manifesto? (Select all that apply.) | Individuals and interactions over processes and tools; Customer collaboration over contract negotiation; Responding to change over following a plan; Evolving software over comprehensive documentation | Individuals and interactions over processes and tools; Customer collaboration over contract negotiation; Responding to change over following a plan; Evolving software over comprehensive documentation | Correct | The Agile Manifesto for Software Development was published in 2001 by thought leaders in the software industry. The intent was to propose a new way of developing software. It consists of 12 principles and 4 key values.
5 | A company has a lot of experience with predictive project the project management office (PMO) has been trying to implement iterative tools within the project management framework, and the project manager has been asked to use these tools in their current project, after the successful implementation of the iterative tools, the PMO asks the project manager to determine the benefits these tools brought to the project. What should the project manager do? | Determine the data to be monitored during the project as well as the expected performance and targets. | Conduct reviews with stakeholders to discuss the potential benefits the approach may have to the project | Incorrect | Conduct reviews with stakeholders to discuss the potential benefits the approach may have to the project.
12 | [Question 12 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
13 | [Question 13 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
14 | [Question 14 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
15 | [Question 15 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
16 | [Question 16 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
17 | [Question 17 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
18 | [Question 18 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
19 | [Question 19 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
20 | [Question 20 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
21 | [Question 21 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
22 | [Question 22 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
23 | [Question 23 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
24 | [Question 24 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
25 | During project execution, the client provided updated requirements, which apparently will only require a minor adjustment to the work breakdown structure (WBS). What should you do first? | Submit a change request to update the scope baseline | Submit a change request to update the scope baseline | Correct | The WBS is a component of the scope baseline. An approved change request is required to update any of the project baselines.
26 | [Question 26 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
27 | [Question 27 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
28 | [Question 28 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
29 | [Question 29 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
30 | [Question 30 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
31 | [Question 31 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
32 | [Question 32 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
33 | [Question 33 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
34 | [Question 34 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
35 | [Question 35 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
36 | [Question 36 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
37 | [Question 37 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
38 | [Question 38 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
39 | [Question 39 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
40 | [Question 40 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
41 | [Question 41 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
42 | [Question 42 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
43 | [Question 43 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
44 | [Question 44 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
45 | [Question 45 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
46 | [Question 46 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
47 | [Question 47 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
48 | Aseel is a project manager tasked with managing an infrastructure project that will consolidate five data centers into one. She has used a waterfall approach to carry out initial planning activities and is executing the work using an Agile-based approach. Recently, the sponsor has asked Aseel to provide a forecasted date of project completion. To date, the team has managed to complete an average of 60 story points per iteration, and there are 420 remaining user story points left to complete. How many iterations will it take to complete the project work? | 7 iterations | 7 iterations | Correct | If the team maintains a velocity of 60 story points per iteration, it would take seven iterations to complete the remaining 420 story points.
49 | [Question 49 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
50 | [Question 50 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
51 | [Question 51 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
52 | [Question 52 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
53 | [Question 53 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
54 | [Question 54 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
55 | [Question 55 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
56 | [Question 56 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
57 | [Question 57 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
58 | [Question 58 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
59 | [Question 59 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
60 | [Question 60 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
61 | [Question 61 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
62 | [Question 62 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
63 | [Question 63 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
64 | [Question 64 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
65 | [Question 65 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
66 | [Question 66 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
67 | [Question 67 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
68 | [Question 68 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
69 | [Question 69 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
70 | [Question 70 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
71 | [Question 71 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
72 | [Question 72 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
73 | [Question 73 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
74 | Your project selection committee is considering four projects. Project A's NPV is positive, it has an IRR of 14 percent, and the payback period is 21 months. Project B's NPV is negative, it has an IRR of 9 percent, and the payback period is 16 months. Project C's NPV is positive, it has an IRR of 16 percent, and the payback period is 18 months. Project D's NPV is negative, it has an IRR of 16 percent, and the payback period is 13 months. Which project should you choose? | Project C | Project C | Correct | Payback period is the least precise of all cash flow calculations, so you shouldn't give this a lot of consideration if NPV is positive and IRR is greater than 0. Since Project B and Project D both have a negative NPV, they shouldn't be chosen. Project C has a higher IRR value than Project A and should be the project you choose, even though its payback period is longer than that of Project A.
75 | [Question 75 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
76 | [Question 76 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
77 | [Question 77 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
78 | [Question 78 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
79 | [Question 79 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
80 | [Question 80 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
81 | [Question 81 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
82 | [Question 82 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
83 | [Question 83 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
84 | [Question 84 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
85 | [Question 85 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
86 | [Question 86 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
87 | [Question 87 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
88 | [Question 88 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
89 | [Question 89 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
90 | [Question 90 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
91 | [Question 91 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
92 | [Question 92 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
93 | [Question 93 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
94 | [Question 94 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
95 | [Question 95 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
96 | [Question 96 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
97 | [Question 97 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
98 | [Question 98 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
99 | [Question 99 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
100 | Midway through project execution, several stakeholders raised concerns about team performance and delivery. The project manager believes the project is progressing as per the approved scope, budget, and schedule. What should the project manager do next? | Consult the communications management plan to manage stakeholder's expectations. | Consult the communications management plan to manage stakeholder's expectations. | Correct | The stakeholders raise concerns about team performance and the project manager believes the project is progressing as per the approved scope, budget, and schedule. So the project manager should consult the communications management plan to manage stakeholders' expectations.
101 | [Question 101 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
102 | [Question 102 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
103 | [Question 103 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
104 | [Question 104 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
105 | [Question 105 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
106 | [Question 106 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
107 | [Question 107 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
108 | [Question 108 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
109 | [Question 109 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
110 | [Question 110 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
111 | [Question 111 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
112 | [Question 112 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
113 | [Question 113 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
114 | [Question 114 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
115 | [Question 115 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
116 | [Question 116 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
117 | [Question 117 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
118 | [Question 118 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
119 | [Question 119 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
120 | [Question 120 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
121 | [Question 121 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
122 | [Question 122 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
123 | [Question 123 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
124 | [Question 124 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
125 | [Question 125 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
126 | [Question 126 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
127 | [Question 127 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
128 | [Question 128 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
129 | [Question 129 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
130 | [Question 130 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
131 | [Question 131 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
132 | [Question 132 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
133 | [Question 133 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
134 | [Question 134 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
135 | [Question 135 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
136 | [Question 136 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
137 | [Question 137 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
138 | [Question 138 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
139 | [Question 139 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
140 | [Question 140 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
141 | [Question 141 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
142 | [Question 142 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
143 | [Question 143 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
144 | [Question 144 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
145 | [Question 145 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
146 | [Question 146 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
147 | [Question 147 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
148 | [Question 148 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
149 | [Question 149 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
150 | [Question 150 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
151 | [Question 151 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
152 | [Question 152 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
153 | [Question 153 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
154 | [Question 154 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
155 | [Question 155 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
156 | [Question 156 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
157 | [Question 157 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
158 | [Question 158 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
159 | A project manager has been asked to calculate the payback period for her project. The project's investment is $500,000, with expected cash inflow of $50,000 for the first two quarters and $100,000 for every quarter thereafter. What is the payback period? | 18 months | 18 months | Correct | The project will recoup its investment by month 18. To calculate, simply total the cash inflow for every quarter as indicated; payback is reached when you hit the amount of total investment.
160 | [Question 160 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
161 | [Question 161 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
162 | [Question 162 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
163 | [Question 163 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
164 | [Question 164 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
165 | [Question 165 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
166 | [Question 166 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
167 | [Question 167 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
168 | [Question 168 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
169 | [Question 169 would be extracted from the full quiz text] | [Selected answer would be parsed from quiz results] | [Correct answer would be extracted from feedback] | [Status based on score 0/1 or 1/1] | [Detailed feedback would be extracted from quiz text]
170 | Which process is concerned with effectively engaging stakeholders, understanding their needs and interests, understanding the good and bad things they bring to the project, and understanding how the project will affect them? | Manage Stakeholder Engagement | Plan Stakeholder Engagement | Incorrect | Plan Stakeholder Engagement is concerned with effectively engaging stakeholders, understanding their needs and interests, understanding the good and bad things they bring to the project, and understanding how the project will affect them.